## Sheet1
Unique id | Risk description | Caused by | Risk owner | Probability | Impact | Risk rating | Controls | Controls owners | Residual probability | Residual Impact | Residual rating
| Bugs in critical functionalities | Software defects | Development Team | High | Medium | Moderate | Robust testing process | QA Team | Medium | Medium | Moderate
| Performance issues during peak usage | System overload | Development Team | High | High | Critical | Load testing, scalable architecture | DevOps Team | Medium | Medium | Severe
| Scope creep | Changing user requirements | Project Manager | Medium | High | Severe | Clear scope, change management protocols | Project Manager | Low | Medium | Moderate
| Unauthorized access to sensitive data | Security vulnerabilities | Security Team | Medium | Very High | Critical | Data encryption, MFA, penetration testing | Security Team | Low | High | Severe
| Low adoption rate | User unfamiliarity | Product Manager | Medium | Medium | Moderate | User training, intuitive design | Training Team | Low | Low | Sustainable
| Budget overruns | Underestimated costs | Product Manager | Medium | Medium | Moderate | Contingency funds, expense tracking | Finance Team | Low | Medium | Moderate
| Delays in resource allocation | Resource unavailability | HR Team | Medium | High | Severe | Flexible timelines, resource backups | Project Manager | Low | Medium | Moderate
| Data loss due to system crashes | Hardware/software failures | IT Team | Low | High | Moderate | Regular backups, recovery systems | IT Team | Low | Low | Sustainable
| Negative feedback on usability | Poor user experience | Design Team | Medium | Medium | Moderate | Beta testing, incorporate user feedback | UX/UI Team | Low | Medium | Moderate
| Post-launch system downtime | Maintenance errors | DevOps Team | Low | Medium | Sustainable | Monitoring tools, dedicated support team | DevOps Team | Very Low | Medium | Sustainable