AMERICAN INTERNATIONAL UNIVERSITY–BANGLADESH (AIUB)

Department of Computer Science
Faculty of Science & Technology (FST)

Fall 2024-25

Section: H, Group: 01

PROJECT TITLE

Virtual Classroom Platform: An Interactive, Accessible, and Engaging Online Learning Environment

Supervised By TONNY SHEKHA KAR

Submitted By

Group Members

| SN | Name | ID |
| --- | --- | --- |
| 1 | AFNAN BIN ISLAM NAHIN | 22-49350-3 |
| 2 | AMAN ULLAH | 22-49345-3 |
| 3 | HRITTIK BHATTACHARJEE | 21-44650-1 |
| 4 | MD. HACHIBUR RAHMAN | 22-46426-1 |
| 5 | WALID BIN KHALED | 22-46101-1 |

Project Estimation (COMOMO)

For our Organic system project , let’s take the number of lines of code to be,

SLOC =20000,

Effort Factor Coefficient = 2.4,

P= 1.05 and

T = 0.38.

We know ,

Effort = PM = Coefficient<Effort Factor>*(SLOC/1000)^P

Effort (PM) = 2.4 x (20000/1000)^1.05

Effort (PM) =55.756

Development time = DM = 2.50*(PM)^T

= 2.50 x (55.756)^0.38

= 11.5220 Months

Required number of people = ST = PM/DM

=55.756/ 11.5220

=4.839 ~ 5

### Human Resource Allocation

| Resource Name | Role | Responsibilities | Skill Set Required | Allocation (Hours/Week) | Duration |
| --- | --- | --- | --- | --- | --- |
| Project Manager | Manager | Plan, monitor, and control project activities, ensure risk management, and QA | Leadership, Communication, PM Tools | 20 | 01/01/2025 - 03/31/2025 |
| Business Analyst | Analyst | Gather requirements, interact with stakeholders, and document user needs | Communication, Analytical, Documentation | 15 | 01/01/2025 - 01/31/2025 |
| UI/UX Designer | Designer | Design platform layout, create interactive prototypes, and improve user experience | Figma, Adobe XD, Creativity | 25 | 02/01/2025 - 02/28/2025 |
| Frontend Developer | Developer | Build UI components, connect APIs, and ensure responsiveness | React.js, HTML/CSS, JavaScript | 30 | 03/01/2025 - 05/31/2025 |
| Backend Developer | Developer | Develop APIs, authentication, and logic for backend services | Node.js, Python, Database Management | 30 | 03/01/2025 - 05/31/2025 |
| Database Administrator | Administrator | Design, implement, and optimize databases | SQL, MongoDB, Backup/Recovery Skills | 20 | 03/01/2025- 05/15/2025. |
| Quality Analyst | Tester | Create and execute test cases, conduct UAT, and debug | Test Automation, Problem-Solving | 25 | 05/01/2025 - 06/15/2025 |
| Deployment Engineer | Engineer | Setup hosting, deploy application, and manage configurations. | AWS, Azure, CI/CD | 20 | 06/01/2025 - 06/15/2025 |
| Trainer | Educator | Conduct training for users and provide documentation | Communication, Training, Documentation | 10 | 06/15/2025 - 06/30/2025 |
| Technical Support Staff | Support | Monitor platform, resolve user issues, and provide updates | Troubleshooting, Communication | 10 | 07/01/2025 - Ongoing |

Environment Resource Allocation

| Environment Type | Purpose | Resources Required | Allocated Duration | Key Dependencies |
| --- | --- | --- | --- | --- |
| Development Environment | For coding, debugging, and integrating components | Workstations, IDEs (e.g., Visual Studio, IntelliJ), GitHub repository, test servers | January 2025 - May 2025 | Version Control, Developer Access |
| Testing Environment | For conducting unit, integration, and user acceptance testing | Test servers, automated testing tools (e.g., Selenium, JMeter), staging databases | April 2025 - June 2025 | QA Team Access, Test Data |
| Staging Environment | Simulates production for final validation before deployment | Staging servers, replica database, network configuration | May 2025 - June 2025 | Final Build, Deployment Approval |
| Production Environment | Live platform for end-users | AWS EC2 instances, S3 storage, SSL certificate, Load balancers | June 2025 - Ongoing | Scheduled Backup Configuration |
| Backup Environment | For data backups and disaster recovery. | Cloud storage, Backup software (e.g., AWS Backup, Azure Backup) | March 2025 - Ongoing | Trainer Access, Training Materials |
| Training Environment | For user training and simulation | simulation. Training servers, replica platform instance, dummy user accounts. | June 2025 | Trainer Access, Training Materials |

Re-usable Software Resource Allocation

| Resource Name | Purpose | Modules/Tasks Used. | Licensing/Ownership. | Allocated Duration |
| --- | --- | --- | --- | --- |
| Node.js | Backend development and API creation | Backend Development (Authentication, APIs) | Open Source | January 2025 - May 2025 |
| React.js | Frontend development for user interface | Dashboard, Chat Interface, Meeting UI | Open Source | January 2025 - May 2025 |
| MySQL | Database management | User Data, Assignments, Exams | Open Source | January 2025 - Ongoing |
| Figma | UI/UX design prototyping | prototyping. Login, Dashboard, Calendar Design. | Freemium | January 2025 - March 2025 |
| AWS Cloud Services | Hosting and storage | Production Environment | Pay-as-you-go | May 2025 - Ongoing |
| Jest | Unit testing for JavaScript code | Frontend and Backend Unit Tests | Open Source | April 2025 - May 2025 |
| Bootstrap/Material UI | UI design framework | Frontend Components (Forms, Buttons) | Open Source | February 2025 - May 2025 |

Risk Analysis: